2010 Work Plan for implementation of Extractive Industries Transparency Initiative

(EITI) in the Republic of Azerbaijan

Agreed by the Multi-Stakeholder Group (MSG) (Government Commission, NGO Coalition, local and foreign companies operating in extractive industries)

| Purpose | Actions | Implementation Period | Executor | Expected Outcome |
| --- | --- | --- | --- | --- |
| - Preparation and disclosure of the 2009 annual EITI report | - MSG launches the reporting period | February 4th | MSG | Regular disclosure of reports in compliance with the EITI principles |
|  | - Placing a tender announcement in the official government newspapers and the website of the State Oil Fund, inviting internationally recognized auditor to participate in aggregation of the annual EITI reports | February 9th | EITI Secretariat |  |
|  | - Sending invitation letters to the internationally recognized auditors to participate in tender | February 11th | Companies Group |  |
|  | - Selection of auditor for aggregation and analysis of EITI reports | February 26th | MSG |  |
|  | - Signing agreement with the Auditor | March 5th | Companies Group |  |
|  | - Sending reporting forms to local and foreign companies | February 26th | Government Commision, EITI Secretariat |  |
|  | - Submission of Government’s, local and foreign companies’ reports to the selected auditor | March 15th | Government Commision, Companies Group |  |
|  | - Disclosure of EITI report and the auditor’s opinion, publication of the report in the official state newspapers and on the websites of the State Oil Fund, the EITI Secretariat of Azerbaijan Republic, NGO Coalition and International Secretariat of EITI | April 16th | MSG, Auditor, EITI Secretariat, NGO Coalition |  |
|  | - NGO Coalition’s presentation of its opinion about the reports to the MSG members, discussion of the reports and taking appropriate decisions by MSG | May 17th | MSG, NGO Coalition, Auditor |  |
| - The preparation and disclosure of the EITI report for the first half of 2010 | - Placing a tender announcement in the official government newspapers and the website of the State Oil Fund, inviting internationally recognized auditor to participate in aggregation of the annual EITI reports | June 14th | EITI Secretariat | Regular disclosure of reports in compliance with the EITI principles |
|  | - Sending invitation letters to the internationally recognized auditors to participate in the tender | June 15th | EITI Secretariat |  |
|  | - Selection of auditor for aggregation and analysis of EITI reports | July 1st | MSG |  |
|  | - Signing an agreement with the Auditor | July 5th | Government Commision |  |
|  | - Sending reporting forms to local and foreign companies | July 7th | Government Commision, EITI Secretariat |  |
|  | - Submission of Government’s, local and foreign companies’ reports to the selected auditor | August 25th | Government Commision, Companies Group |  |
|  | - Disclosure of the EITI report and the Auditor’s opinion, publication of the report in the official state newspapers and on the websites of the State Oil Fund, the EITI Secretariat of Azerbaijan Republic, NGO Coalition and International Secretariat of EITI | September 27th | MSG, Auditor, EITI Secretariat, NGO Coalition |  |
|  | - NGO Coalition’s presentation of its opinion about the reports throughout the year to the MSG members, discussion of the reports and appropriate decisions by MSG | October 20th | MSG, NGO Coalition, Auditor |  |
| - Minimize repeated errors in the reporting cycle | - Presentation on the units of measurement of associated and non-associated gas by Companies Group | April 15th | MSG, Companies Group | Improvement of the EITI process in Azerbaijan |
| - In line with current developments, review suggestions for ammendment of EITI memorandum | - Presentation of the proposed ammendments by the NGO Coalition, discussion of these suggestions and taking appropriate decisions | April 16th | MSG, NGO Coalition | Improvement of the EITI process in Azerbaijan |
| - Review suggestion to the Companies to disaggregate their reports | - Discussion of possible transition to disagregated reporting and associated issues and taking appropriate decisions | May 17th | MSG, NGO Coalition | Improvement of the EITI process in Azerbaijan |
| - Outreach initiatives to increase awareness about EITI process in Azerbaijan and abroad | - Discussion of the ways to increase awareness about EITI (conferences, seminars, round tables, television programs, publications, exchange programs etc). | September 27th | MSG, EITI Secretariat | Increased awareness about EITI process in society, peer learning |

Note: All the suggestions should be communicated to all the MSG members not later than 10 business days prior to the corresponding discussion.